## Backlog
ID | Sprint | Sprint Focus | Start | Due | Title | Area | Type | Priority | Est. (h) | Files / Path | Acceptance criteria | Status | Owner | Notes
1 | Sprint 1 | Security & auth hardening | 2026-02-02 | 2026-02-03 | Return after 'User already exists' in createUser | Auth | Bug | Critical | 1 | backend/controllers/userController.js | Registering with an existing email returns a single 400 JSON response, no user is saved, and no 'Cannot set headers after they are sent' error appears in the log. | Not started
2 | Sprint 1 | Security & auth hardening | 2026-02-02 | 2026-02-03 | Send 401 on failed login instead of hanging | Auth | Bug | Critical | 1 | backend/controllers/userController.js | Unknown email or wrong password returns 401 {message:'Invalid email or password'}; the request never hangs open. | Not started
3 | Sprint 1 | Security & auth hardening | 2026-02-02 | 2026-02-04 | Remove console.log of email and plaintext password | Security | Bug | Critical | 0.5 | backend/controllers/userController.js | No credential values appear in server logs for any auth request. | Not started
4 | Sprint 1 | Security & auth hardening | 2026-02-02 | 2026-02-04 | Fix 'httyOnly' typo in logout cookie options | Auth | Bug | High | 0.5 | backend/controllers/userController.js | Logout clears the jwt cookie with correct httpOnly flag; a follow-up /profile call returns 401. | Not started
5 | Sprint 1 | Security & auth hardening | 2026-02-02 | 2026-02-05 | Strip password hashes from GET /api/users response | Security | Bug | High | 0.5 | backend/controllers/userController.js | getAllUsers uses .select('-password'); no hash field is present in the admin user list payload. | Not started
6 | Sprint 1 | Security & auth hardening | 2026-02-02 | 2026-02-05 | Add global errorHandler and notFound middleware | Backend | Chore | High | 3 | backend/middlewares/, backend/index.js | Unmatched routes return 404 JSON; thrown errors return the intended status code with a stack trace only in development. | Not started
7 | Sprint 1 | Security & auth hardening | 2026-02-02 | 2026-02-06 | Rewrite asyncHandler to forward errors instead of always 500 | Backend | Bug | High | 1.5 | backend/middlewares/asyncHandler.js | A controller that sets res.status(404) before throwing responds 404, not 500. | Not started
8 | Sprint 1 | Security & auth hardening | 2026-02-02 | 2026-02-06 | Fix checkId to call next(error) for invalid ObjectId | Backend | Bug | Medium | 1 | backend/middlewares/checkId.js | GET /api/products/abc returns a clean 404 JSON instead of an unhandled synchronous throw. | Not started
9 | Sprint 1 | Security & auth hardening | 2026-02-02 | 2026-02-09 | Validate required env vars at boot and fail fast | Backend | Chore | High | 1.5 | backend/index.js, backend/config/db.js | Missing MONGO_URI or JWT_SECRET exits with a named error before the server starts listening. | Not started
10 | Sprint 1 | Security & auth hardening | 2026-02-02 | 2026-02-09 | Fix cookie secure flag so local HTTP login works | Auth | Bug | High | 1 | backend/utils/createToken.js | Cookie is secure only when NODE_ENV==='production'; login works over http://localhost and stays secure in production. | Not started
11 | Sprint 1 | Security & auth hardening | 2026-02-02 | 2026-02-10 | Rate limit login and registration endpoints | Security | Feature | High | 2 | backend/routes/userRoutes.js | express-rate-limit caps /api/users/auth at 5 attempts per 15 min per IP and returns 429 with a retry hint. | Not started
12 | Sprint 1 | Security & auth hardening | 2026-02-02 | 2026-02-10 | Add helmet and a configured CORS allowlist | Security | Feature | High | 2 | backend/index.js | helmet is enabled and CORS accepts credentials only from origins in the CLIENT_URL allowlist. | Not started
13 | Sprint 1 | Security & auth hardening | 2026-02-02 | 2026-02-11 | Sanitize input against NoSQL injection | Security | Feature | High | 2 | backend/index.js | express-mongo-sanitize is wired in; posting {"email":{"$gt":""}} to /api/users/auth returns 400, not a session. | Not started
14 | Sprint 1 | Security & auth hardening | 2026-02-02 | 2026-02-11 | Add schema validation for auth request bodies | Backend | Feature | Medium | 4 | backend/middlewares/validate.js, backend/routes/userRoutes.js | zod schemas reject malformed register/login bodies with 400 and a field-level error list. | Not started
15 | Sprint 1 | Security & auth hardening | 2026-02-02 | 2026-02-12 | Enforce password strength and normalize emails | Auth | Feature | Medium | 2 | backend/controllers/userController.js, backend/models/userModel.js | Passwords under 8 chars are rejected; emails are lowercased and trimmed before the uniqueness check. | Not started
16 | Sprint 1 | Security & auth hardening | 2026-02-02 | 2026-02-12 | Shorten JWT lifetime and add a refresh token flow | Auth | Feature | Medium | 6 | backend/utils/createToken.js, backend/controllers/userController.js | Access token expires in 1 day, a refresh cookie renews it, and logout invalidates both. | Not started
17 | Sprint 1 | Security & auth hardening | 2026-02-02 | 2026-02-13 | Add .env.example for backend and frontend | DevOps | Docs | Medium | 1 | backend/.env.example, frontend/.env.example | Both files list every required variable with a safe placeholder; real .env files stay gitignored. | Not started
18 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-16 | Fix 'createAt' typo in fetchAllProducts sort | Backend | Bug | Medium | 0.5 | backend/controllers/productController.js | Sort uses createdAt so /api/products/allproducts actually returns newest-first. | Not started
19 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-17 | Implement real pagination in fetchProducts | Backend | Feature | High | 3 | backend/controllers/productController.js | Endpoint honours ?page=, applies .skip(), and returns accurate page, pages and hasMore values. | Not started
20 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-17 | Wire product list UI to the new pagination API | Frontend | Feature | High | 3 | frontend/src/redux/api/productApiSlice.js, frontend/src/pages/Shop.jsx | Shop and Home pass the page param and render working prev/next controls. | Not started
21 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-18 | Attach the uploaded image path when creating a product | Backend | Bug | Critical | 2 | backend/controllers/productController.js, frontend/src/pages/Admin/ProductList.jsx | Creating a product with an upload saves the image field; the model's required-image validation no longer rejects the save. | Not started
22 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-18 | Fix Windows backslashes in the upload response path | Backend | Bug | High | 1 | backend/routes/uploadRoutes.js | Response returns /uploads/name.jpg with forward slashes on Windows so <img src> resolves. | Not started
23 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-19 | Create the uploads directory at boot if missing | Backend | Bug | Medium | 0.5 | backend/index.js | A fresh clone can accept an image upload without a manual mkdir. | Not started
24 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-19 | Add a multer file-size limit and clear error | Security | Feature | Medium | 1 | backend/routes/uploadRoutes.js | Files over 2MB are rejected with 400 and a readable message instead of filling disk. | Not started
25 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-20 | Guard updateProductDetails against a missing product | Backend | Bug | High | 1.5 | backend/controllers/productController.js | Updating a non-existent id returns 404; the redundant second save() call is removed. | Not started
26 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-20 | Delete the image file from disk when a product is removed | Backend | Feature | Medium | 2 | backend/controllers/productController.js | Removing a product unlinks its uploads file and tolerates an already-missing file. | Not started
27 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-20 | Replace deprecated findByIdAndRemove in removeCategory | Backend | Bug | High | 1 | backend/controllers/categoryController.js | Category deletion uses findByIdAndDelete and returns 404 when the id does not exist. | Not started
28 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-23 | Block deleting a category that still has products | Backend | Feature | High | 3 | backend/controllers/categoryController.js | Deleting an in-use category returns 409 with the product count; an optional reassign target is supported. | Not started
29 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-23 | Validate the filterProducts request body | Backend | Bug | High | 1.5 | backend/controllers/productController.js | POST /api/products/filtered-products with an empty body returns 400 instead of a 500 from reading .length of undefined. | Not started
30 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-24 | Reconcile quantity vs countInStock on the product model | Backend | Chore | High | 3 | backend/models/productModel.js, backend/controllers/productController.js | One field is the source of truth for stock; admin forms, order creation and the UI all read the same field. | Not started
31 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-24 | Add GET /api/category root listing and fix route ordering | Backend | Bug | Medium | 1 | backend/routes/categoryRoutes.js | Listing categories works at the root path and the /categories literal never gets shadowed by /:id. | Not started
32 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-25 | Add a text index for product search | Backend | Feature | Medium | 2 | backend/models/productModel.js | name, brand and description are indexed; keyword search uses the index instead of an unanchored regex scan. | Not started
33 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-25 | Add server-side sorting options for the product list | Backend | Feature | Medium | 3 | backend/controllers/productController.js | ?sort=price_asc¦price_desc¦newest¦rating returns correctly ordered results. | Not started
34 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-26 | Support multiple images per product | Feature | Feature | Medium | 6 | backend/models/productModel.js, frontend/src/pages/Products/ProductDetails.jsx | Products store an images array; the detail page shows a thumbnail gallery with a main image swap. | Not started
35 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-26 | Add a unique slug field to products | SEO | Feature | Low | 3 | backend/models/productModel.js, frontend/src/main.jsx | Products are reachable at /product/:slug with the id route kept as a redirect. | Not started
36 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-27 | Compress uploads and generate thumbnails with sharp | Backend | Feature | Medium | 4 | backend/routes/uploadRoutes.js | Every upload is resized to max 1200px and a 300px thumbnail is written alongside it. | Not started
37 | Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-27 | Write a seed script for categories, products and an admin user | DevOps | Feature | Medium | 3 | backend/seeder.js | npm run seed populates a clean database; npm run seed:destroy clears it. | Not started
38 | Sprint 3 | Orders, payments & data integrity | 2026-03-02 | 2026-03-02 | Protect the sales analytics routes with admin auth | Security | Bug | Critical | 1.5 | backend/routes/orderRoutes.js | total-orders, total-sales and total-sales-by-date require authenticate + authorizeAdmin and return 401 anonymously. | Not started
39 | Sprint 3 | Orders, payments & data integrity | 2026-03-02 | 2026-03-03 | Add an ownership check to findOrderById | Security | Bug | Critical | 2 | backend/controllers/orderController.js | A signed-in user requesting another user's order id gets 403; admins still see every order. | Not started
40 | Sprint 3 | Orders, payments & data integrity | 2026-03-02 | 2026-03-04 | Verify PayPal payments server-side before marking paid | Payments | Feature | Critical | 6 | backend/controllers/orderController.js, backend/utils/paypal.js | The order is only marked paid after the capture id is verified against the PayPal API and the amount matches totalPrice. | Not started
41 | Sprint 3 | Orders, payments & data integrity | 2026-03-02 | 2026-03-04 | Restrict markOrderAsPaid to the order owner | Security | Bug | Critical | 1.5 | backend/controllers/orderController.js | PUT /api/orders/:id/pay by a non-owner returns 403 and leaves isPaid unchanged. | Not started
42 | Sprint 3 | Orders, payments & data integrity | 2026-03-02 | 2026-03-04 | Guard req.body.payer access in markOrderAsPaid | Backend | Bug | High | 1 | backend/controllers/orderController.js | A pay request without a payer object returns 400 rather than throwing on undefined. | Not started
43 | Sprint 3 | Orders, payments & data integrity | 2026-03-02 | 2026-03-05 | Fix createOrder crash when orderItems is missing | Backend | Bug | High | 1 | backend/controllers/orderController.js | POST /api/orders with no orderItems returns 400 'No order items' instead of a 500 from .map on undefined. | Not started
44 | Sprint 3 | Orders, payments & data integrity | 2026-03-02 | 2026-03-06 | Decrement stock atomically when an order is created | Backend | Feature | Critical | 4 | backend/controllers/orderController.js | Stock is reduced in the same transaction as the order write; two concurrent orders cannot oversell the last unit. | Not started
45 | Sprint 3 | Orders, payments & data integrity | 2026-03-02 | 2026-03-06 | Reject orders containing out-of-stock items | Backend | Feature | High | 3 | backend/controllers/orderController.js | Ordering more than countInStock returns 400 naming the offending product; nothing is written. | Not started
46 | Sprint 3 | Orders, payments & data integrity | 2026-03-02 | 2026-03-06 | Move tax rate, shipping fee and free-shipping threshold to config | Backend | Chore | Medium | 2 | backend/controllers/orderController.js, backend/config/pricing.js | The hardcoded 0.15, 100 and 10 come from config/env and are covered by a unit test. | Not started
47 | Sprint 3 | Orders, payments & data integrity | 2026-03-02 | 2026-03-09 | Store money as integer minor units instead of toFixed strings | Backend | Chore | Medium | 6 | backend/models/orderModel.js, backend/controllers/orderController.js | Totals are stored as integers (tiyin/cents); no float rounding drift appears across cart, order and analytics. | Not started
48 | Sprint 3 | Orders, payments & data integrity | 2026-03-02 | 2026-03-10 | Rename the calcualteTotalSalesByDate typo | Backend | Chore | Low | 1 | backend/controllers/orderController.js, backend/routes/orderRoutes.js | The export, route handler and any frontend reference use the corrected spelling. | Not started
49 | Sprint 3 | Orders, payments & data integrity | 2026-03-02 | 2026-03-10 | Paginate and filter the admin order list | Backend | Feature | Medium | 3 | backend/controllers/orderController.js | GET /api/orders supports page, limit and status filters and returns total counts. | Not started
50 | Sprint 3 | Orders, payments & data integrity | 2026-03-02 | 2026-03-10 | Paginate the customer order history endpoint | Backend | Feature | Medium | 2 | backend/controllers/orderController.js | /api/orders/mine returns paged results sorted newest-first. | Not started
51 | Sprint 3 | Orders, payments & data integrity | 2026-03-02 | 2026-03-11 | Add an order status enum with valid transitions | Feature | Feature | High | 5 | backend/models/orderModel.js, backend/controllers/orderController.js | Orders carry pending¦paid¦shipped¦delivered¦cancelled; invalid transitions are rejected with 400. | Not started
52 | Sprint 3 | Orders, payments & data integrity | 2026-03-02 | 2026-03-12 | Let customers cancel an unpaid order and restock it | Feature | Feature | Medium | 4 | backend/controllers/orderController.js, frontend/src/pages/User/UserOrder.jsx | Cancelling an unpaid order sets status cancelled and returns the reserved quantity to stock. | Not started
53 | Sprint 3 | Orders, payments & data integrity | 2026-03-02 | 2026-03-12 | Send an order confirmation email | Feature | Feature | Medium | 5 | backend/utils/mailer.js, backend/controllers/orderController.js | A successful order triggers a templated email with the item list and total; failures are logged, not fatal. | Not started
54 | Sprint 3 | Orders, payments & data integrity | 2026-03-02 | 2026-03-12 | Generate a downloadable PDF invoice for paid orders | Feature | Feature | Medium | 6 | backend/controllers/orderController.js, frontend/src/pages/Orders/Order.jsx | GET /api/orders/:id/invoice streams a PDF with order lines, tax, shipping and total for the owner or an admin. | Not started
55 | Sprint 3 | Orders, payments & data integrity | 2026-03-02 | 2026-03-13 | Add a local payment provider (Payme/Click) for UZS | Payments | Feature | High | 10 | backend/routes/paymentRoutes.js, frontend/src/pages/Orders/PlaceOrder.jsx | A customer can pay in UZS end to end in sandbox; webhook callbacks mark the order paid idempotently. | Not started
56 | Sprint 4 | Frontend state & checkout | 2026-03-16 | 2026-03-17 | Fix the RTK Query tag mismatch ('Products' vs 'Product') | Frontend | Bug | High | 1 | frontend/src/redux/api/productApiSlice.js | providesTags matches the declared tagTypes so creating a product refreshes the list without a hard reload. | Not started
57 | Sprint 4 | Frontend state & checkout | 2026-03-16 | 2026-03-17 | Change deleteProduct from providesTags to invalidatesTags | Frontend | Bug | High | 0.5 | frontend/src/redux/api/productApiSlice.js | Deleting a product immediately removes it from the admin list. | Not started
58 | Sprint 4 | Frontend state & checkout | 2026-03-16 | 2026-03-18 | Add invalidatesTags to updateProduct and createReview | Frontend | Bug | Medium | 1 | frontend/src/redux/api/productApiSlice.js | Editing a product or posting a review refreshes the detail page without a manual refetch. | Not started
59 | Sprint 4 | Frontend state & checkout | 2026-03-16 | 2026-03-18 | Move localStorage writes out of cart reducers | Frontend | Chore | Medium | 3 | frontend/src/redux/features/cart/cartSlice.js, frontend/src/redux/store.js | Reducers stay pure; persistence happens in a store subscriber and cart state still survives a reload. | Not started
60 | Sprint 4 | Frontend state & checkout | 2026-03-16 | 2026-03-19 | Fix the no-op resetCart reducer | Frontend | Bug | Medium | 1 | frontend/src/redux/features/cart/cartSlice.js | Dispatching resetCart actually clears items, address and payment method, and clears the persisted copy. | Not started
61 | Sprint 4 | Frontend state & checkout | 2026-03-16 | 2026-03-19 | Handle 401 responses globally by logging out | Frontend | Feature | High | 3 | frontend/src/redux/api/apiSlice.js | An expired session clears auth state, shows a toast and redirects to /login instead of failing silently. | Not started
62 | Sprint 4 | Frontend state & checkout | 2026-03-16 | 2026-03-20 | Drive the API base URL from an env variable | DevOps | Chore | High | 2 | frontend/src/redux/constants.js, frontend/vite.config.js | Dev keeps the proxy; production builds call VITE_API_URL, with no localhost:5000 left in the bundle. | Not started
63 | Sprint 4 | Frontend state & checkout | 2026-03-16 | 2026-03-20 | Pass the PayPal clientId into PayPalScriptProvider | Payments | Bug | High | 2 | frontend/src/main.jsx, frontend/src/pages/Orders/Order.jsx | The SDK loads with the clientId from /api/config/paypal and the buttons render on the order page. | Not started
64 | Sprint 4 | Frontend state & checkout | 2026-03-16 | 2026-03-23 | Add an ErrorBoundary and a 404 route | Frontend | Feature | Medium | 3 | frontend/src/main.jsx, frontend/src/components/ErrorBoundary.jsx | An unknown URL renders a styled 404 page and a render error shows a recovery screen instead of a blank page. | Not started
65 | Sprint 4 | Frontend state & checkout | 2026-03-16 | 2026-03-23 | Delete src_backup_before_redesign and the .bak files | Chore | Chore | Medium | 0.5 | frontend/src_backup_before_redesign/, frontend/*.bak | The dead backup folder and .bak files are removed from the repo and the app still builds. | Not started
66 | Sprint 4 | Frontend state & checkout | 2026-03-16 | 2026-03-24 | Add inline validation to Login and Register | Frontend | Feature | Medium | 3 | frontend/src/pages/Auth/Login.jsx, frontend/src/pages/Auth/Register.jsx | Empty, malformed or mismatched fields show field-level messages before any request is sent. | Not started
67 | Sprint 4 | Frontend state & checkout | 2026-03-16 | 2026-03-24 | Debounce the header search and cancel stale requests | Frontend | Feature | Medium | 2 | frontend/src/pages/Auth/Navigation.jsx | Typing fires at most one request per 300ms and out-of-order responses never overwrite newer results. | Not started
68 | Sprint 4 | Frontend state & checkout | 2026-03-16 | 2026-03-25 | Persist favorites per user account instead of shared localStorage | Feature | Feature | Medium | 5 | backend/models/userModel.js, frontend/src/redux/features/favorites/favoriteSlice.js | Favorites follow the signed-in account across devices; guests keep a local list that merges on login. | Not started
69 | Sprint 4 | Frontend state & checkout | 2026-03-16 | 2026-03-25 | Add a quantity stepper capped at available stock | Frontend | Feature | Medium | 2 | frontend/src/pages/Cart.jsx | Quantity cannot exceed countInStock and the cart shows a clear message when the cap is hit. | Not started
70 | Sprint 4 | Frontend state & checkout | 2026-03-16 | 2026-03-26 | Guard the checkout route against an empty cart | Frontend | Bug | Medium | 2 | frontend/src/pages/Orders/PlaceOrder.jsx, frontend/src/pages/Orders/Shipping.jsx | Visiting /placeorder with an empty cart or missing address redirects instead of rendering a broken summary. | Not started
71 | Sprint 4 | Frontend state & checkout | 2026-03-16 | 2026-03-26 | Make the price breakdown consistent across cart, checkout and order | Frontend | Chore | Medium | 3 | frontend/src/pages/Cart.jsx, frontend/src/pages/Orders/PlaceOrder.jsx, frontend/src/pages/Orders/Order.jsx | Items, tax, shipping and total are formatted by one shared helper and match the server totals exactly. | Not started
72 | Sprint 4 | Frontend state & checkout | 2026-03-16 | 2026-03-27 | Replace moment with dayjs | Chore | Chore | Low | 2 | frontend/package.json, frontend/src/pages/ | No moment import remains, dates render identically, and the bundle drops by roughly 60KB. | Not started
73 | Sprint 5 | UX, performance & accessibility | 2026-03-30 | 2026-03-31 | Add route-level code splitting | Performance | Feature | Medium | 4 | frontend/src/main.jsx | Admin and checkout routes load as separate chunks behind Suspense; the initial bundle shrinks measurably. | Not started
74 | Sprint 5 | UX, performance & accessibility | 2026-03-30 | 2026-03-31 | Lazy-load apexcharts on the admin dashboard only | Performance | Chore | Medium | 2 | frontend/src/pages/Admin/AdminDashboard.jsx | The charting library is absent from the storefront bundle and the dashboard still renders its graphs. | Not started
75 | Sprint 5 | UX, performance & accessibility | 2026-03-30 | 2026-04-01 | Lazy-load product images with explicit dimensions | Performance | Chore | Medium | 2 | frontend/src/pages/Products/, frontend/src/pages/Home.jsx | Images use loading='lazy' with width/height set; cumulative layout shift on Home drops below 0.1. | Not started
76 | Sprint 5 | UX, performance & accessibility | 2026-03-30 | 2026-04-01 | Add skeleton loaders to Home, Shop and ProductDetails | Frontend | Feature | Low | 3 | frontend/src/components/Skeleton.jsx | Each page shows a skeleton matching its final layout instead of a bare spinner. | Not started
77 | Sprint 5 | UX, performance & accessibility | 2026-03-30 | 2026-04-02 | Make the admin tables usable on mobile | Frontend | Feature | Medium | 4 | frontend/src/pages/Admin/ | User, product and order tables stack into cards below 768px with no horizontal scroll. | Not started
78 | Sprint 5 | UX, performance & accessibility | 2026-03-30 | 2026-04-02 | Add visible keyboard focus states throughout | Accessibility | Feature | High | 3 | frontend/src/index.css, frontend/src/pages/Auth/Navigation.jsx | Every interactive element has a visible focus ring and the whole checkout is completable by keyboard. | Not started
79 | Sprint 5 | UX, performance & accessibility | 2026-03-30 | 2026-04-03 | Add alt text and aria-labels for icon-only controls | Accessibility | Feature | High | 2 | frontend/src/components/, frontend/src/pages/Products/HeartIcon.jsx | Screen readers announce every icon button and product image meaningfully. | Not started
80 | Sprint 5 | UX, performance & accessibility | 2026-03-30 | 2026-04-03 | Fix colour-contrast failures found by Lighthouse | Accessibility | Chore | Medium | 3 | frontend/src/index.css, frontend/tailwind.config.js | Lighthouse accessibility scores 90+ on Home, Shop and Cart with no contrast violations. | Not started
81 | Sprint 5 | UX, performance & accessibility | 2026-03-30 | 2026-04-06 | Add per-route meta titles and descriptions | SEO | Feature | Medium | 3 | frontend/src/pages/ | Each route sets a unique title, description and Open Graph image via react-helmet-async. | Not started
82 | Sprint 5 | UX, performance & accessibility | 2026-03-30 | 2026-04-07 | Generate sitemap.xml and robots.txt | SEO | Feature | Low | 2 | frontend/public/, backend/routes/ | Both files are served in production and list every public product and category URL. | Not started
83 | Sprint 5 | UX, performance & accessibility | 2026-03-30 | 2026-04-07 | Add multi-language support (uz / ru / en) | Feature | Feature | High | 8 | frontend/src/i18n/, frontend/src/pages/ | All UI strings come from translation files, the language persists across reloads, and no hardcoded copy remains in components. | Not started
84 | Sprint 5 | UX, performance & accessibility | 2026-03-30 | 2026-04-08 | Add UZS currency support and locale-aware formatting | Feature | Feature | High | 4 | frontend/src/Utils/format.js, backend/config/pricing.js | Prices render in the selected currency with correct grouping; the stored value stays in one base currency. | Not started
85 | Sprint 5 | UX, performance & accessibility | 2026-03-30 | 2026-04-08 | Show related products on the detail page | Feature | Feature | Medium | 3 | frontend/src/pages/Products/ProductDetails.jsx, backend/controllers/productController.js | The detail page shows up to 4 same-category products excluding the current one. | Not started
86 | Sprint 5 | UX, performance & accessibility | 2026-03-30 | 2026-04-09 | Add a recently viewed products strip | Feature | Feature | Low | 3 | frontend/src/pages/Home.jsx, frontend/src/Utils/localStorage.js | The last 8 viewed products appear on Home, deduplicated and capped. | Not started
87 | Sprint 5 | UX, performance & accessibility | 2026-03-30 | 2026-04-09 | Add a low-stock alert widget to the admin dashboard | Feature | Feature | Medium | 3 | frontend/src/pages/Admin/AdminDashboard.jsx, backend/controllers/productController.js | Products under a configurable stock threshold are listed with a direct link to edit each one. | Not started
88 | Sprint 5 | UX, performance & accessibility | 2026-03-30 | 2026-04-10 | Build a review moderation queue for admins | Feature | Feature | Medium | 5 | backend/controllers/productController.js, frontend/src/pages/Admin/ | Admins can approve, hide or delete reviews; only approved reviews count toward the product rating. | Not started
89 | Sprint 6 | Testing, CI/CD & deployment | 2026-04-13 | 2026-04-14 | Set up Jest and Supertest with an in-memory MongoDB | Testing | Feature | High | 4 | backend/package.json, backend/tests/setup.js | npm test runs against mongodb-memory-server and passes on a clean clone; the placeholder test script is gone. | Not started
90 | Sprint 6 | Testing, CI/CD & deployment | 2026-04-13 | 2026-04-15 | Unit test calcPrices, cartUtils and the auth middleware | Testing | Feature | High | 4 | backend/tests/unit/, frontend/src/Utils/ | Tax, shipping threshold, cart totals and token rejection paths are covered, including boundary values. | Not started
91 | Sprint 6 | Testing, CI/CD & deployment | 2026-04-13 | 2026-04-16 | Integration test the full auth flow | Testing | Feature | High | 4 | backend/tests/integration/auth.test.js | Register, login, profile read, profile update and logout are covered, plus duplicate-email and bad-password cases. | Not started
92 | Sprint 6 | Testing, CI/CD & deployment | 2026-04-13 | 2026-04-17 | Integration test the order lifecycle | Testing | Feature | High | 5 | backend/tests/integration/orders.test.js | Create, pay, deliver and cancel are covered along with the ownership and stock-rejection paths. | Not started
93 | Sprint 6 | Testing, CI/CD & deployment | 2026-04-13 | 2026-04-20 | Set up Vitest and React Testing Library | Testing | Feature | Medium | 4 | frontend/package.json, frontend/src/tests/ | Cart reducer, format helpers and the Login form render and assert correctly under npm test. | Not started
94 | Sprint 6 | Testing, CI/CD & deployment | 2026-04-13 | 2026-04-21 | Add a Playwright end-to-end checkout test | Testing | Feature | High | 6 | e2e/checkout.spec.js | Browse, add to cart, sign in, ship, pay in sandbox and see the confirmation all pass headlessly in CI. | Not started
95 | Sprint 6 | Testing, CI/CD & deployment | 2026-04-13 | 2026-04-23 | Add a GitHub Actions CI pipeline | DevOps | Feature | High | 4 | GITHUB/workflows/ci.yml | Every pull request runs lint, backend tests, frontend tests and a production build, and blocks merge on failure. | Not started
96 | Sprint 6 | Testing, CI/CD & deployment | 2026-04-13 | 2026-04-24 | Add Prettier, lint-staged and a pre-commit hook | DevOps | Feature | Medium | 2 | package.json, .prettierrc, .husky/ | Staged files are formatted and linted before commit; the repo is fully formatted in one baseline commit. | Not started
97 | Sprint 6 | Testing, CI/CD & deployment | 2026-04-13 | 2026-04-27 | Add Dockerfile and docker-compose for the whole stack | DevOps | Feature | Medium | 5 | Dockerfile, docker-compose.yml | docker compose up starts MongoDB, the API and the built frontend, and the app is reachable on one port. | Not started
98 | Sprint 6 | Testing, CI/CD & deployment | 2026-04-13 | 2026-04-28 | Serve the frontend build from Express in production | DevOps | Feature | Medium | 2 | backend/index.js | In production the API serves the Vite build and falls back to index.html for client-side routes. | Not started
99 | Sprint 6 | Testing, CI/CD & deployment | 2026-04-13 | 2026-04-29 | Write the root README | Docs | Docs | High | 4 | README.md | Covers setup, env vars, npm scripts, API route table, folder structure and a deployment section with screenshots. | Not started
100 | Sprint 6 | Testing, CI/CD & deployment | 2026-04-13 | 2026-04-30 | Add structured logging and a health check endpoint | DevOps | Feature | Medium | 3 | backend/index.js, backend/utils/logger.js | pino logs requests with a request id and GET /api/health reports uptime plus database connectivity. | Not started

## Sprint Plan
Sprint plan - Feb 2 to Apr 30, 2026
Every figure below is a live formula over the Backlog sheet.
Sprint | Focus | Start | End | Tasks | Est. (h) | Critical | High | Done | % Done
Sprint 1 | Security & auth hardening | 2026-02-02 | 2026-02-13 | 17 | 30.5 | 3 | 9 | 0 | 0%
Sprint 2 | Products, categories & uploads | 2026-02-16 | 2026-02-27 | 20 | 45 | 1 | 8 | 0 | 0%
Sprint 3 | Orders, payments & data integrity | 2026-03-02 | 2026-03-13 | 18 | 64 | 5 | 5 | 0 | 0%
Sprint 4 | Frontend state & checkout | 2026-03-16 | 2026-03-27 | 17 | 36 | 0 | 5 | 0 | 0%
Sprint 5 | UX, performance & accessibility | 2026-03-30 | 2026-04-10 | 16 | 54 | 0 | 4 | 0 | 0%
Sprint 6 | Testing, CI/CD & deployment | 2026-04-13 | 2026-04-30 | 12 | 47 | 0 | 7 | 0 | 0%
TOTAL | Full Feb-Apr backlog | 2026-02-02 | 2026-04-30 | 100 | 276.5 | 9 | 38 | 0 | 0%
Breakdown by area
Area | Tasks | Est. (h) | Share of hours
Accessibility | 3 | 8 | 2.893%
Auth | 6 | 11.5 | 4.159%
Backend | 29 | 63 | 22.78%
Chore | 2 | 2.5 | 0.9042%
DevOps | 8 | 22 | 7.957%
Docs | 1 | 4 | 1.447%
Feature | 12 | 57 | 20.61%
Frontend | 15 | 34.5 | 12.48%
Payments | 3 | 18 | 6.51%
Performance | 3 | 8 | 2.893%
SEO | 3 | 8 | 2.893%
Security | 9 | 13 | 4.702%
Testing | 6 | 27 | 9.765%

## How to use
How to use this backlog
Backlog for | github.com/Azizbeccoder/E-commerce-web_site (MERN e-commerce: Express + MongoDB API, React + Redux Toolkit + Vite frontend)
Window | February 2 - April 30, 2026, split into six two-week sprints.
How it was built | Every item was written against the actual code in the repo. Bug items name a real defect found in a specific file; feature and chore items build on what already exists.
Columns you edit | Status, Owner, Notes. Everything else is reference.
Status values | Not started / In progress / In review / Blocked / Done (dropdown)
Priority values | Critical / High / Medium / Low (dropdown; Critical and High are colour-coded)
Est. (h) | Rough solo-developer estimate in hours. Adjust freely - the Sprint Plan totals recalculate.
Sprint Plan tab | Live COUNTIF/SUMIF formulas over the Backlog sheet. Change a Status to Done and the % Done column updates.
Example row | Row 2: ID 1, Sprint 1, due 2026-02-02, 'Return after User already exists in createUser', Auth / Bug / Critical, 1.0h - set Status to 'In progress' and put your name in Owner.
Assumptions | Estimates assume one full-time developer and no team velocity data was available - they are the author's judgement, not measured. Due dates are spread evenly across each sprint's business days rather than dependency-ordered.
Sprint 1 rationale | Auth and error-handling defects come first because several of them (missing return on duplicate signup, silent hang on failed login, plaintext password logging) affect every request path underneath.
Sprint 3 rationale | Payment verification and stock decrement are grouped because both are order-write concerns and touch the same controller.